## Main-Report
Boost Foundation Project Minuwangamuwa Report
|  | NGO |  | FutureCare
|  | Project name |  | Primary School Minuwangamuwa
|  | CRM-code(s) |  | To be determined
|  | Project manager |  | Remco Scherpenzeel
|  | Contact person Boost |  | Ian Upton / Erudini Smits
|  | Short description |  | Rennovation and rebuilding of primary school and delivery of basic educational materals and needs
|  | Project phase |  | 300-1000 |  | Average % completion | 30.77%
|  | Starting date |  | tbd |  | Planned date of completoin | tbd | 42542
|  | Current report date |  | 2017-10-04 16:55 |  | Reporting frequency | Every two weeks | wekelijks
Most important news
Overall:
-
Planning Status
-
Budget status
Financial |  | Budget (Prognosis) |  |  | Actual Project Status
|  | Material | Labour | Totaal Budget | Budget Spent | Budget needed | Final Prognosis | Reasons / Description / Details
Install and repair entrance |  | 1620 |  | 1620 |  | 1620 | 1620
Install waterworks and fix WC |  | 1780 |  | 1780 |  | 1780 | 1780
Repair floor |  | 1830 |  | 1830 |  | 1830 | 1830
Repair windows and wire meshes |  | 1620 |  | 1620 |  | 1620 | 1620
Repair walls, gutters and windows |  | 1570 |  | 1570 |  | 1570 | 1570
Place partisan walls |  | 1150 |  | 1150 |  | 1150 | 1150
Repair playground |  | 1245 |  | 1245 |  | 1245 | 1245
Fix library and furniture. Buy teaching equipment and school supplies |  | 1240 |  | 1240 |  | 1240 | 1240
Sub total |  | 12055 | 0 | 12055 | 0 | 12055 | 12055
Risk mitigation
Risk mitigation (25% rounded) |  | 3013.75 | 0 | 3013.75 |  | 3013.75 | 3013.75
Exchange rate (5%) |  | 602.75 | 0 | 602.75 |  | 602.75 | 602.75
Materials (10%) |  | 1205.5 |  | 1205.5 |  | 1205.5 | 1205.5
Labour |  | 0 | 1750 | 1750 |  | 1750 | 1750
None |  | 0 | 0 | 0 |  | 0 | 0
Sub total |  | 0 | 0 | 6572 |  | 6572 | 6572
Total |  | 16877 | 1750 | 18627 | 0 | 18627 | 18627
Project Phases
Phase |  |  | Start Date | End Date | Milestones
000 | Financials and Contracting
100 | Scoping and Selecting
200 | Contracts
300 | Install and repair entrance
400 | Install waterworks and fix WC
500 | Repair floor
600 | Repair windows and wire meshes
700 | Repair walls, gutters and windows
800 | Place partisan walls
900 | Repair playground
1000 | Fix library and furniture. Buy teaching equipment and school supplies
1100 | Closing Project
Risks
Impact | Ergency/ Chance |  | Risk Description |  |  | Risk Mitigation |  |  | Risk Owner
high | high | high | Corruption due to lack of transparency |  |  | financial agreement FutureCare - Periodic payments on completion bimonthly meeting and financial update with photographic evidence vouchers for when other receipts are unavailable |  |  | Remco Scherpenzeel
high | high | high | Exchange rate fluctuation |  |  | We need to put a margin on estimate to make sure that the exchange rate does not affect our project. |  |  | Remco Scherpenzeel
high | high | high | Long term maintenance |  |  | We build with easy maintenance in mind. The responsibility for maintenance will be placed upon the principal of the school. |  |  | Remco Scherpenzeel
high | high | high | Budgeted materials are not enough |  |  | We will calculate 10% risk mitigation. |  |  | Remco Scherpenzeel
high | high | high | High labour costs |  |  | We will get volunteers to do the work. |  |  | Remco Scherpenzeel
high | high | high | We don't get any volunteers to do the labour |  |  | We will calculate the full amount of labour costs as risk mitigation. |  |  | Remco Scherpenzeel
high | high | high | We don't have the funding on time and miss our timeframe window |  |  | Need to discuss with partner |  |  | Remco Scherpenzeel
high | high | high | registration hours of work workers |  |  | The headmaster of the school is in charge of registering the workers hours. FutureCare visits the site every Monday to check progress FutureCare reports on progress in the biweekly (with photographic evidence |  |  | Remco Scherpenzeel
high | high | high | extra pricing for raw materials and labour because "white person" is involved |  |  | Second opinions asked in the neighbouring village, resulting in change of the work force and material supplier |  |  | Remco Scherpenzeel
ISSUE'S
Priority | Sub product |  | Issue Description |  |  | Mitigation |  |  | Issue Owner
Activities in the coming period
Decision moments/Topics
Date | Decision Documents |  | Topic |  |  | Outcome |  |  | Decision makers (Min. 2)

## Traffic Light
Money
Quality
Products
Resources
Time
Status Trend
Description / Action
Transition
Process
Tools

## Project Details
Legend | STATUS | The Status has to be determined with a board member of Boost
| Red | Critical path and running behind schedule or above budget
| Orange | Slightly running behind schedule or above budget (non critical)
| Green | On time / Budget no issues
Product Overview
DP nr | Description | % completion | Status | Comments / Date of completion
000 | Financials and Contracting | 100%
10 | Financial rules | 100% | G
12 | Project governance in place | 100% | G
100 | Scoping and Selecting | 100%
110 | Visit and photo's | 100% | G
111 | Meeting with locals | 100% | G
200 | Contracts | 100%
210 | Explain contract to Local NGO | 100% | G
213 | Sign Contract and return copy | 100% | G
300 | Install Water System | 0%
311 | Buy Materials | 0% | G
312 | Instruct workers | 0% | G
313 | Check completion | 0% | G
314 | Pay Workers | 0% | G
400 | Install and repair Toilets | 0%
410 | Buy Materials | 0% | G
411 | Instruct workers | 0% | G
412 | Check completion | 0% | G
413 | Pay Workers | 0% | G
500 | Repave entrance to school | 100%
510 | Buy Materials | 100% | G
511 | Instruct workers | 100% | G
512 | Check completion | 100% | G
513 | Pay Workers | 100% | G
600 | Rebuild Staircase | 0%
610 | Buy Materials | 0% | G
611 | Instruct workers | 0% | G
612 | Check completion | 0% | G
613 | Pay Workers | 0% | G
700 | Build Library | 0%
710 | Buy Materials | 0% | G
711 | Instruct workers | 0% | G
712 | Check completion | 0% | G
713 | Pay Workers | 0% | G
800 | Build Playground | 0%
810 | Buy Materials | 0% | G
811 | Instruct workers | 0% | G
812 | Check completion | 0% | G
813 | Pay Workers | 0% | G
900 | Childrens school supplies | 0%
910 | Buy Supplies | 0% | G
911 | Hand out Supplies (photo) | 0% | G
1000 | Teaching Equipment | 0%
1010 | Buy Equipment | 0% | G
1011 | Install Equipment | 0% | G
1100 | Closing Project | 0%
1110 | Photo Evidence | 0% | G
1111 | Evaluation from School | 0% | G
1113 | Project Evalution Boost | 0% | G
1114 | Closing Financial Report | 0% | G
1115 | Newsletter and Report to funder | 0% | G
30.77%