## Main-Report
Boost Foundation Project Pittawella Report
|  | NGO |  | FuturCare
|  | Project name |  | Primary School Pitawela
|  | CRM-code(s) |  | To be determined
|  | Project manager |  | Roderik Loodewijks / Remco Scherpenzeel
|  | Contact person Boost |  | Ian Upton / Erudini Smits
|  | Short description |  | Rennovation and rebuilding of primary school and delivery of basic educational materals and needs
|  | Project phase |  | 400-800 |  | Average % completion | 31.12%
|  | Starting date |  | 2016-05-01 |  | Planned date of completoin | 31-11-2016 | 42542
|  | Current report date |  | 2016-05-13 09:14 |  | Reporting frequency | Every two weeks | wekelijks
Most important news
Overall:
- Agreed upon and signed contract with our Sri Lankan partner FutureCare (Ramani Smits) - Signed financial agreement and transferred €1500,- to FuturCare according to financial agreement - Spoke to local contractors and bought raw materails for the build - Spoke with megan the futur project manager to apply for our oversee's volunteer programme.
Planning Status
- overall planning is green, we decided to repave the enterance first which makes it easier to transport the equiptment needed for the build of the water supplies and toilets
Budget status
- Funds diverted from supplies and teaching equiptment for completion of the repaving the entrance to the school (motion to be voted on in meeting 11-5-2016)
Financial |  | Budget (Prognosis) |  |  | Actual Project Status
|  | Material | Labour | Totaal Budget | Budget Spent | Budget needed | Final Prognosis | Reasons / Description / Details
Install Water System |  | 400 | 100 | 500 | 500 |  | 500
Install and repair Toilets |  | 500 | 250 | 750 | 750 |  | 750
Repave entrance to school |  | 500 | 1000 | 1500 | 1500 | 750 | 2250 | Terrible state, needed to build additional wall
Rebuild Staircase |  | 500 | 500 | 1000 | 1000 |  | 1000
Build Library |  | 400 | 100 | 500 | 500 |  | 500
Build Playground |  | 500 | 500 | 1000 | 1000 | 0 | 1000
Childrens school supplies |  | 750 | 0 | 750 | 750 | -500 | 250 | fund diversion towards repaving enterance
Teaching Equipment |  | 500 | 0 | 500 | 500 | -250 | 250 | fund diversion towards repaving enterance
0
0
Sub total |  | 4050 | 2450 | 6500 | 6500 | 0 | 6500
Other costs and expenses
none |  | 0 | 0 | 0 | 0 | 0 | 0
None |  | 0 | 0 | 0 | 0 | 0 | 0
None |  | 0 | 0 | 0 | 0 | 0 | 0
Sub total |  | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 4050 | 2450 | 6500 | 6500 | 0 | 6500
Project Phases
Phase |  |  | Start Date | End Date | Milestones
000 | Financials and Contracting |  | 2016-04-15 | 2016-05-01 | Financial agreement written and signed by board and futurecare
100 | Scoping and Selecting |  | 2016-04-15 | 2016-05-01 | Local workers selected and definitive scope has been defined
200 | Contracts |  | 2016-04-15 | 2016-05-01 | All contrats signed by all parties
300 | Install Water System |  | 2016-06-01 | 2016-07-01
400 | Install and repair Toilets |  | 2016-07-01 | 2016-08-01
500 | Repave entrance to school |  | 2016-05-01 | 2016-06-01 | Raw materials ordered, workers instructed and enterance has been cleared
600 | Rebuild Staircase |  | 2016-05-01 | 2016-06-01 | Raw materials ordered
700 | Build Library |  | 2016-08-01 | 2016-09-01
800 | Build Playground |  | 2016-09-01 | 2016-10-01
900 | Childrens school supplies |  | 2016-10-01 | 2016-11-01
1000 | Teaching Equipment |  | 2016-10-01 | 2016-11-01
1100 | Closing Project |  | 2016-11-01 | 2016-12-01
Risks
Impact | Ergency/ Chance |  | Risk Description |  |  | Risk Mitigation |  |  | Risk Owner
high | high | high | Corruption due to lack of transparency |  |  | financial agreement FutureCare - Periodic payments on completion bimonthly meeting and financial update with photographic evidence vouchers for when other receipts are unavailable |  |  | Ian Upton
high | high | high | registration hours of work workers |  |  | The headmaster of the school is in charge of registering the workers hours. FutureCare visits the site every Monday to check progress FutureCare reports on progress in the biweekly (with photographic evidence |  |  | Ian Upton
high | high | high | extra pricing for raw materials and labour because "white person" is involved |  |  | Second opinions asked in the neighbouring village, resulting in change of the work force and material supplier |  |  | Ian Upton
ISSUE'S
Priority | Sub product |  | Issue Description |  |  | Mitigation |  |  | Issue Owner
medium | 500 Repave enterance to school |  | The enterance to the school was in very bad shape meaning it will cost more than planned |  |  | funds will be diverted from 900 and 1000 to mitigate the cost. An extra fund raiser will have to be initiated for the school supplies |  |  | Ian Upton
Activities in the coming period
- repaving the entrance to the school and the staircase to the second building are going to be the main priority (this could take up more resources than planned as the situation was worse than expected) - water supply will be initiated after the enterance is repaved, this way we can easily transport the building materials to where they are needed.
Decision moments/Topics
Date | Decision Documents |  | Topic |  |  | Outcome |  |  | Decision makers (Min. 2)
2016-05-10 | project report |  | Divert funds to repave the enterance

## Traffic Light
Money
Quality
Products
Resources
Time
Status Trend
Description / Action
. On Schedule
Transition
Process
Diverted funds to repaveing of school
. less funds for school materials, fundraiser needed.
. On par
. on par
. not applicable
. not appicable
Tools

## Project Details
Legend | STATUS | The Status has to be determined with a board member of Boost
| Red | Critical path and running behind schedule or above budget
| Orange | Slightly running behind schedule or above budget (non critical)
| Green | On time / Budget no issues
Product Overview
DP nr | Description | % completion | Status | Comments / Date of completion
000 | Financials and Contracting | 100%
10 | Financial rules | 100% | G | 2016-05-01
12 | Project governance in place | 100% | G | 2016-05-01
100 | Scoping and Selecting | 100%
110 | Visit and photo's | 100% | G | 2016-05-01
111 | Meeting with locals | 100% | G | 2016-05-01
200 | Contracts | 100%
210 | Explain contract to Local NGO | 100% | G | 2016-05-01
213 | Sign Contract and return copy | 100% | G | 2016-05-01
300 | Install Water System | 0%
311 | Buy Materials | 0% | G
312 | Instruct workers | 0% | G
313 | Check completion | 0% | G
314 | Pay Workers | 0% | G
400 | Install and repair Toilets | 0%
410 | Buy Materials | 0% | G
411 | Instruct workers | 0% | G
412 | Check completion | 0% | G
413 | Pay Workers | 0% | G
500 | Repave entrance to school | 51.25%
510 | Buy Materials | 80% | o | more materials needed
511 | Instruct workers | 100% | G
512 | Check completion | 0% | G
513 | Pay Workers | 25% | o | more manhours needed
600 | Rebuild Staircase | 51.25%
610 | Buy Materials | 80% | o | more materials needed
611 | Instruct workers | 100% | G
612 | Check completion | 0% | G
613 | Pay Workers | 25% | o | more manhours needed
700 | Build Library | 0%
710 | Buy Materials | 0% | G
711 | Instruct workers | 0% | G
712 | Check completion | 0% | G
713 | Pay Workers | 0% | G
800 | Build Playground | 0%
810 | Buy Materials | 0% | G
811 | Instruct workers | 0% | G
812 | Check completion | 0% | G
813 | Pay Workers | 0% | G
900 | Childrens school supplies | 0%
910 | Buy Supplies | 0% | o | funds diverted
911 | Hand out Supplies (photo) | 0% | G
1000 | Teaching Equipment | 0%
1010 | Buy Equipment | 0% | o | funds diverted
1011 | Install Equipment | 0% | G
1100 | Closing Project | 2%
1110 | Photo Evidence | 10% | G
1111 | Evaluation from School | 0% | G
1113 | Project Evalution Boost | 0% | G
1114 | Closing Financial Report | 0% | G
1115 | Newsletter and Report to funder | 0% | G
31.12%