Weekly Meeting Minutes 01/06/2016

Attended: Ian, Remco, Justin, Salome, Osman and Erudini

Absent: Roderick

Meeting commenced at 19:00 (01/06/2016)

**Project Update:**

1. Sharing Knowledge project: shared a fb post and will send out flyers next week.
2. Building a future project: The retaining wall is completed but due to the heavy rains most of the soil was washed away so to start building the road they first need to gather new soil. Which is planned to happen this week.
3. Equal chances project: No updates
4. Emergency project: Need to talk to Ramani and made a concrete project plan

**Financial Update:**

* Ian found another donator willing to give €6500
* Justin is rewriting the financial budget – cashflow

**IT Update:**

* We have access to Office 365
* We will also be able to start the Google advertising/promotion soon. (Ian will contact Wietse about this when we get the a green flag)

**Communication Update:**

* Osman launched the ‘Donate a like’ campaign and its going well
* The Press release was sent to OGD
* Sjoerd’s report is online (website)

**Vounteering Update:**

* Remco met with Tijmen and they had a brainstorm session which resulted in a conversation about two friends (doctors) in Tanzania who do volunteer work and could maybe use some help. This is still a very fresh idea and will be discussed later on with Roderick.
* Spoke to Mila (potential volunteer), who is interested in working with Boost. She has done volunteer work before in Ghana where she had a crowd funding and rebuilt a school. She also travels a lot to write blogs and articles about the different cultures and her experience. Mila also has connections with ‘get it done’ organization which is a crowd funding platform. (they are also partnered with ‘why donate’)
* Salome found a volunteer that would be willing to help with handing out flyers.

**Announcements:**

* Next Monthly meeting starts at 11am at OGD Delft this Sunday
* Ramani Smits (CEO of FutureCare) and Megan Punselie (potential volunteer) will be invited to the monthly meeting.

**Progress on action points:**

Look at the action list for all new actions and the progress of current actions.